## Sheet1
Andrew Seltzman |  |  | Canceled |  |  | Andrew Seltzman
LCC4700 Thesis timeline |  |  | Planed Date |  |  | LCC4700 Thesis timeline
Mark 3 fusion reactor |  |  | Actual Date |  |  | Mark 3 fusion reactor
Stage 1 Testing
[6 empty] | Jan | Jan | Jan | Feb | Feb | Feb | Feb | Mar | Mar | Mar | Mar | Mar | Apr | Apr | Apr | Apr
Task | Title | Description | Requires | Finish Date | Done | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 2 | 9 | 16 | 23 | 30 | 6 | 13 | 20 | 27
1 | Bellows mt | Machine VH to Core mount |  | 2008-01-14 | bar: Jan 13
2 | 12v pwr mt | Mount 12v power supply |  | 2008-01-15 | bar: Jan 13
3 | CF base | Machine carbon fiber reactor base |  | 2008-01-14 | bar: Jan 13
4 | PTFE Base | Line base with HV insulation | 3 | 2008-01-14 | bar: Jan 13
5 | HV adapt | Machine HV adaptor for grid |  | 2008-01-26 | bar: Jan 13; Jan 27
6 | Coolant res | Build GCL coolant reservoir |  | => Stage 2 | bar: Jan 13 to Jan 20
7 | Coolant tube | Connect GCL to coolant feed sys |  | 2008-02-10 | bar: Jan 13; Jan 27 to Feb 10
8 | Therm mon | Connect thermocouples to cooling sys |  | 2008-01-15 | bar: Jan 13 to Jan 20
9 | Coolant test | Test coolant system | 7,8 | 2008-02-15 | bar: Jan 13; Feb 10
10 | Core bari | Install core convectron transducer |  | => Stage 2 | bar: Jan 13
11 | Man evac | Connect manifold evacuation tube |  | 2008-01-27 | bar: Jan 13; Jan 27
12 | D2 MFC | Install deuterium mass flow controller |  | 2008-01-27 | bar: Jan 13; Jan 27
13 | Ion ECRF | Construct remaining ion injectors | 12 | => Stage 2 | bar: Jan 13 to Jan 20
14 | Ion extr | Mount injector extractor cones |  | => Stage 2 | bar: Jan 20
15 | Low vac test | Gross leak check on core | 10,11,12,13 | 2008-02-16 | bar: Jan 13 to Jan 20; Feb 10
16 | Turbo hookup | Connect turbo pump to vacuum system |  | 2008-02-22 | bar: Jan 20; Feb 17
17 | High vac test | High vacuum check of core | 15,16 | 2008-02-22 | bar: Jan 20; Feb 17 to Mar 2
18 | HV mon test | High voltage supply test |  | 2008-02-20 | bar: Jan 13 to Jan 20; Feb 10 to Feb 24
19 | Neu mod | Moderator installation on 10BF3 tube |  | 2008-01-19 | bar: Jan 13
20 | Rad cal | ORS calibration of x-ray detectors |  | 2008-01-18 | bar: Jan 13
21 | Neu cal | ORS calibration of neutron detectors | 19 | 2008-01-24 | bar: Jan 20
22 | Ion split | ECRF splitter installation |  | => Stage 2 | bar: Jan 20
23 | Ion vco | ECRF VCO and mixer assembly |  | => Stage 2 | bar: Jan 20
24 | Ion bias | Test ion bias supply |  | => Stage 2 | bar: Jan 20
25 | Ion test | Test injector system | 13,14,17,24 | => Stage 2 | bar: Jan 20
26 | AC pow | Complete AC bus wiring |  | 2008-02-15 | bar: Jan 20 to Feb 10
27 | ECU | Install control system |  | Mar | bar: Jan 27; Feb 24 to Mar 16
28 | LV8 test | Test labview control interface | 26,27 | Mar | bar: Jan 27; Feb 24 to Mar 16
29 | Core cam | install core camera |  | => Stage 2 | bar: Jan 27
30 | Move | Move reactor to RCZ for testing |  | 2008-03-26 | bar: Jan 27; Mar 23
31 | Rad block | Install neutron and x-ray shielding |  | 2008-03-27 | bar: Jan 27; Mar 23
32 | Rad svy | ORS radiation survey per RS-4A | 30,31 | 2008-03-27 | bar: Jan 27; Mar 23
33 | CR ops | Commence reactor operation | 30,31,32 | 2008-03-27 | bar: Jan 27; Mar 23
34 | Neu meter | Neutron measurement system integration |  | => Stage 2 | bar: Jan 27
35 | Grid data | Collect grid temperature data |  | 2008-04-25 | bar: Feb 3 to Feb 17; Mar 23 to Apr 27
36 | Ion data | Collect injector data |  | => Stage 2 | bar: Feb 10 to Feb 24
37 | TS laser | Mount Thompson scattering laser |  | => Stage 2 | bar: Feb 10 to Feb 17
38 | TS detect | Mount Thompson scattering detector |  | => Stage 2 | bar: Feb 10 to Feb 17
39 | TS control | Build Thompson scattering control |  | => Stage 2 | bar: Feb 17 to Feb 24
40 | Pmap | Map plasma temperature profile |  | => Stage 2 | bar: Feb 17 to Mar 2
41 | Thesis draft | Thesis draft |  | 2008-03-10 | bar: Mar 9
42 | Ind meet | Individual meeting |  | 2008-03-31 | bar: Mar 30
43 | urop Present | Present at UROP fair |  | 2008-04-03 | bar: Mar 30
44 | ECE Present | Present at ECE fair |  | 2008-04-11 | bar: Apr 13
45 | Ths Present | Present thesis |  | 2008-04-30 | bar: Apr 20
46 | Draft revision | Revise thesis draft |  | 2008-05-01 | bar: Apr 20 to Apr 27
47 | Thesis sub | Submit and upload thesis |  | 2008-05-02 | bar: Apr 27